## Summary
Phase | Task Count
Phase 1 - Discovery & Inventory | 6
Phase 2 - Design & Governance | 5
Phase 3 - Pilot Migration | 5
Phase 4 - Wave-based Cutover | 6
Phase 5 - Access & Topics Application | 4
Phase 6 - Validation & Handover | 4
TOTAL | 30

## Migration Plan
S.No | Phase | Description | Status
1 | Phase 1 - Discovery | Extract full inventory of ADO org via REST API: projects, repos, default branches, branch policies, size, contributors, last-commit date | Not Started
2 | Phase 1 - Discovery | Identify repo-name collisions across ADO projects (same repo name in multiple projects). Flag for suffix decision | Not Started
3 | Phase 1 - Discovery | Export ADO permissions: project-level groups, team memberships, per-repo overrides | Not Started
4 | Phase 1 - Discovery | Snapshot each repo locally via ghorg or scripted clone as pre-migration safety net | Not Started
5 | Phase 1 - Discovery | Inventory current branch policies per repo (required reviewers, min approvers, build validation, status checks, path filters) | Not Started
6 | Phase 1 - Discovery | Publish discovery workbook (this file + Repo Inventory sheet) to stakeholders for sign-off | Not Started
7 | Phase 2 - Design | Confirm GHEC tenant setup: standard GHEC (not EMU), Entra SSO + SCIM configured | Not Started
8 | Phase 2 - Design | Define topic taxonomy: project-*, tier-*, type-*, tech-* (controlled vocabulary in a CSV) | Not Started
9 | Phase 2 - Design | Define team taxonomy: <project>-admins / -maintainers / -writers / -readers + platform-admins + security-readers | Not Started
10 | Phase 2 - Design | Author Ruleset JSON library: default-protected, release-branches, hotfix, databricks-uat. Store in github-config repo | Not Started
11 | Phase 2 - Design | Map ADO permissions -> GitHub repo roles (Read / Triage / Write / Maintain / Admin). Document mapping table | Not Started
12 | Phase 3 - Pilot | Select 2 low-risk repos from 2 different ADO projects for pilot | Not Started
13 | Phase 3 - Pilot | Run gh ado2gh migrate-repo in dry-run then live for pilots; validate Git history, tags, PRs | Not Started
14 | Phase 3 - Pilot | Apply topics, teams, and default Ruleset to pilot repos | Not Started
15 | Phase 3 - Pilot | Validate access with real users from each mapped role; capture friction | Not Started
16 | Phase 3 - Pilot | Retro on pilot; adjust scripts, topic list, Ruleset JSON before scaling | Not Started
17 | Phase 4 - Cutover | Group remaining repos into waves of ~15-20 by project + risk tier | Not Started
18 | Phase 4 - Cutover | For each wave: freeze ADO writes (deny push via ADO policy), notify stakeholders 48h prior | Not Started
19 | Phase 4 - Cutover | Run gh ado2gh migrate-repo in batch for the wave; monitor GEI queue | Not Started
20 | Phase 4 - Cutover | Verify each migrated repo: commit SHA parity, branch count, tag count, open PR count | Not Started
21 | Phase 4 - Cutover | Redirect any consumers (submodules, CI clone URLs, package feeds) to new GitHub URL | Not Started
22 | Phase 4 - Cutover | Archive the ADO repo (read-only) once wave validation is green | Not Started
23 | Phase 5 - Apply | Bulk-apply topics per repo via gh api (project-*, tier-*, type-*, tech-*) from discovery workbook | Not Started
24 | Phase 5 - Apply | Bulk-create teams and assign repo permissions via gh api (dry-run first) | Not Started
25 | Phase 5 - Apply | Attach Rulesets to repos matching topic patterns (e.g. topic:project-a -> default-protected) | Not Started
26 | Phase 5 - Apply | Configure CODEOWNERS files where per-path review is required | Not Started
27 | Phase 6 - Validation | Run full audit: every repo has >=1 project-* topic, correct default branch, at least one Ruleset attached | Not Started
28 | Phase 6 - Validation | Security review: no repo left public unintentionally, secret-scanning + push-protection enabled org-wide | Not Started
29 | Phase 6 - Validation | Hand over runbook to platform team: adding a new repo, adding a topic, requesting access | Not Started
30 | Phase 6 - Validation | Sunset ADO org (retain as read-only archive for defined period, then decommission) | Not Started

## Tooling
Tool | Owner | Purpose | License | Recommendation
GitHub Enterprise Importer (gh ado2gh) | GitHub official | Repos + history + PRs + wiki + work items ADO -> GHEC | MIT / included with GHEC | Primary migration tool
gh CLI + gh api | GitHub official | Bulk topics, teams, permissions, Rulesets | MIT | Primary automation post-migration
ADO REST API + Python | Microsoft | Extract discovery inventory from ADO side | Free | Discovery phase
ghorg | gabrie30 (community) | Bulk clone/backup entire ADO org | Apache-2.0 | Pre-migration safety snapshot
git-filter-repo | Elijah Newren | History rewrite (strip secrets, split monorepos) before migration | MIT | Only if pre-migration cleanup needed
BFG Repo-Cleaner | rtyley | Simpler alternative to git-filter-repo | GPL-3.0 | Optional alternative
Terraform integrations/github | GitHub | Declarative repos/teams/protection as code | MPL-2.0 | Optional; overkill for one-time cutover
ado2gh Ruby gem (mona-actions) | GitHub PS community | Batch orchestration wrappers over GEI | MIT | Optional convenience

## Repo Inventory
S.No | ADO Project | ADO Repo Name | Default Branch | Size (MB) | Contributors | Last Commit Date | Current Branch Policies | Target GitHub Repo Name | Collision? | Target Topics | Target Team(s) | Wave # | Status
1 | ProjectA | payments-service | main |  |  |  | 2 reviewers, build required | payments-service | No | project-a, tier-1, service | project-a-writers, project-a-admins | 1 | Not Started
2 | ProjectA | shared-lib | main |  |  |  | 1 reviewer | shared-lib | Check | project-a, library | project-a-writers | 1 | Not Started
3 | ProjectB | shared-lib | master |  |  |  | no policy | shared-lib-projectb | Yes (rename) | project-b, library | project-b-writers | 2 | Not Started
4 | ProjectB | databricks-etl | main |  |  |  | 1 reviewer, path filter on notebooks/* | databricks-etl | No | project-b, databricks, data, tier-1 | project-b-writers, data-platform | 2 | Not Started

## Topic Taxonomy
Topic | Category | Meaning / Rule
project-a | Project | Repo belongs to former ADO Project A. Exactly one project-* topic per repo (mandatory).
project-b | Project | Repo belongs to former ADO Project B.
tier-1 | Tier | Business-critical, production-serving. Strictest Ruleset.
tier-2 | Tier | Internal / supporting. Standard Ruleset.
tier-3 | Tier | Experimental / sandbox. Minimal protection.
service | Type | Deployable service.
library | Type | Consumed by other repos.
infrastructure | Type | Terraform / Bicep / IaC.
data | Type | Data pipelines, ETL, notebooks.
docs | Type | Documentation-only repo.
databricks | Tech | Databricks notebooks / DLT / jobs.
terraform | Tech | Terraform modules or stacks.
dotnet | Tech | .NET codebase.
python | Tech | Python codebase.
node | Tech | Node.js / TypeScript.

## Access Model
GitHub Team | Repo Role | Purpose
<project>-admins | Admin | Full control incl. settings, secrets, Rulesets. Small group.
<project>-maintainers | Maintain | Manage issues/PRs/releases, cannot change repo settings.
<project>-writers | Write | Push to non-protected branches; PRs into protected.
<project>-readers | Read | Clone / view only.
platform-admins | Org Owner (subset) | Cross-cutting platform team. Owns github-config repo.
security-readers | Security Manager | Read + security alerts across all repos.