## Summary
Item | Detail
Client | Amalgamated Bank (Abank)
Source | Azure DevOps Server on-prem (abdevopsdev, API 5.1)
Target | GitHub Enterprise Cloud (Standard)
Total Repos | 327
Active Repos to Migrate | 309 (18 empty repos excluded, confirmed skip)
ADO Projects | 24
Migration Approach | git push mirror from VDI. GEI not supported for on-prem ADO Server.
Batch Size | 10 repos per batch
Total Batches | 31
Total Phases | 8 (Phase 0 through Phase 7)
Planned Start | 14 Jul 2026
Planned End | 31 Aug 2026
Total Duration | Approx. 7 weeks (weekends excluded)

## Roadmap
S.No | Phase | Activity | Description | Start Date | End Date | Status | Expected Output
1 | Phase 0 | Kickoff and Governance | Align all stakeholders on scope, migration approach, and timeline. Decisions needed: master to main rename, 18 empty repos skip, 3 repo name conflicts, and PR history acceptance. | 14 Jul 2026 | 14 Jul 2026 | In Progress | Scope sign-off and decision log
2 | Phase 0 | Inventory Finalization | Confirm the 309 active repos, agree on batch groupings, resolve the 3 collision renames, and confirm disposition of the 18 empty repos. | 15 Jul 2026 | 15 Jul 2026 | Not Started | Finalized Repo Inventory with batch assignments
3 | Phase 1 | Script - Mirror Migration | Build git_mirror_migrate.py to clone each repo from ADO and push it to GitHub. Includes dry-run mode, retry on failure, resume capability, and the master to main rename option. | 16 Jul 2026 | 21 Jul 2026 | Not Started | git_mirror_migrate.py ready
4 | Phase 1 | Script - Topics and Teams | Build apply_topics_teams.py to set GitHub topics and team permissions for each repo based on the workbook. Dry-run and idempotent. | 16 Jul 2026 | 21 Jul 2026 | Not Started | apply_topics_teams.py ready
5 | Phase 1 | Script - Branch Rulesets | Build apply_rulesets.py with 3 to 4 Ruleset JSON templates covering default protection, require review, file size, and comment required. Rulesets are attached by topic. | 16 Jul 2026 | 21 Jul 2026 | Not Started | apply_rulesets.py and JSON templates ready
6 | Phase 1 | Script - Post-Migration Verify | Build post_migration_verify.py to run a pass or fail check on each repo covering branch count, default branch, topics, team access, and Ruleset attachment. | 17 Jul 2026 | 22 Jul 2026 | Not Started | post_migration_verify.py ready
7 | Phase 1 | Script - CI/CD Template Applicator | Develop the standard GitHub Actions workflow YAML for identified repos. Build apply_cicd.py to push this template to each repo automatically. | 17 Jul 2026 | 22 Jul 2026 | Not Started | cicd_template.yml and apply_cicd.py ready
8 | Phase 1 | Self-Hosted Runner Setup | Register an org-level self-hosted runner on Abank infrastructure. Validate that the runner comes online in the GitHub org and successfully picks up workflow jobs. | 16 Jul 2026 | 22 Jul 2026 | Not Started | Runner registered and online in GitHub org
9 | Phase 1 | Script Testing on Sandbox | Test all scripts against the zeb-ai sandbox org. Validate dry-run, retry, resume, and error handling for each script before using on Abank repos. | 22 Jul 2026 | 23 Jul 2026 | Not Started | All scripts passing on sandbox
10 | Phase 2 | Pilot - 2 Repos | Run the full end-to-end sequence on 2 repos: one from ScriptRefactoring and one stale single-repo project. Steps are mirror, topics, Ruleset, CI/CD, and verify. Repo owner validates the result. | 23 Jul 2026 | 24 Jul 2026 | Not Started | 2 repos on GitHub, verify passing
11 | Phase 2 | Pilot Review and Fix | Review what gaps were found in the pilot. Fix scripts and update the runbook. Get written sign-off to proceed to batch migration. | 24 Jul 2026 | 27 Jul 2026 | Not Started | Updated scripts, runbook, and sign-off
12 | Phase 3 | Batch 1 - Repos 1 to 10 | Stale single-repo projects last active more than 2 years ago. Send 24 hours freeze notice, mirror, apply topics and Ruleset, verify, then archive in ADO. | 27 Jul 2026 | 28 Jul 2026 | Not Started | 10 repos on GitHub, ADO archived
13 | Phase 3 | Batch 2 - Repos 11 to 20 | Single-repo projects last active 1 to 2 years ago. Same freeze, mirror, topics, Ruleset, verify, archive process. | 28 Jul 2026 | 29 Jul 2026 | Not Started | 10 repos on GitHub, ADO archived
14 | Phase 3 | Batch 3 - Repos 21 to 30 | SSIS ETL repos (5) and remaining single-repo projects. Same process as Batch 1. | 29 Jul 2026 | 30 Jul 2026 | Not Started | 10 repos on GitHub, ADO archived
15 | Phase 3 | Batch 4 - Repos 31 to 40 | Non Binary repos (2) and active single-repo projects. Send 24 hours freeze notice before starting. | 30 Jul 2026 | 31 Jul 2026 | Not Started | 10 repos on GitHub, ADO archived
16 | Phase 3 | Batch 5 - Repos 41 to 50 | Remaining active single-repo projects. Send 24 hours freeze notice before starting. | 31 Jul 2026 | 31 Jul 2026 | Not Started | 10 repos on GitHub, ADO archived
17 | Phase 4 | Batch 6 - Repos 51 to 60 | ScriptRefactoring project, first 10 repos. Send 24 hours freeze notice before starting. | 04 Aug 2026 | 05 Aug 2026 | Not Started | 10 SR repos on GitHub
18 | Phase 4 | Batch 7 - Repos 61 to 70 | ScriptRefactoring project, next 10 repos. | 05 Aug 2026 | 06 Aug 2026 | Not Started | 10 SR repos on GitHub
19 | Phase 4 | Batch 8 - Repos 71 to 80 | ScriptRefactoring project, next 10 repos. | 06 Aug 2026 | 06 Aug 2026 | Not Started | 10 SR repos on GitHub
20 | Phase 4 | Batch 9 - Repos 81 to 90 | ScriptRefactoring project, next 10 repos. | 06 Aug 2026 | 07 Aug 2026 | Not Started | 10 SR repos on GitHub
21 | Phase 4 | Batch 10 - Repos 91 to 106 | ScriptRefactoring project, final 16 repos. All ScriptRefactoring repos now on GitHub. | 07 Aug 2026 | 12 Aug 2026 | Not Started | All 56 SR repos on GitHub
22 | Phase 5 | Batch 11 - Repos 107 to 116 | AB AppDev project begins. First 10 repos ordered by oldest last commit. Send 24 hours freeze notice before starting. | 12 Aug 2026 | 12 Aug 2026 | Not Started | 10 AB AppDev repos on GitHub
23 | Phase 5 | Batch 12 - Repos 117 to 126 | AB AppDev project, next 10 repos. | 12 Aug 2026 | 13 Aug 2026 | Not Started | 10 AB AppDev repos on GitHub
24 | Phase 5 | Batch 13 - Repos 127 to 136 | AB AppDev project, next 10 repos. | 13 Aug 2026 | 14 Aug 2026 | Not Started | 10 AB AppDev repos on GitHub
25 | Phase 5 | Batch 14 - Repos 137 to 146 | AB AppDev project, next 10 repos. | 14 Aug 2026 | 17 Aug 2026 | Not Started | 10 AB AppDev repos on GitHub
26 | Phase 5 | Batch 15 - Repos 147 to 156 | AB AppDev project, next 10 repos. | 17 Aug 2026 | 18 Aug 2026 | Not Started | 10 AB AppDev repos on GitHub
27 | Phase 5 | Batch 16 - Repos 157 to 166 | AB AppDev project, next 10 repos. | 18 Aug 2026 | 18 Aug 2026 | Not Started | 10 AB AppDev repos on GitHub
28 | Phase 5 | Batch 17 - Repos 167 to 176 | AB AppDev project, next 10 repos. | 18 Aug 2026 | 19 Aug 2026 | Not Started | 10 AB AppDev repos on GitHub
29 | Phase 5 | Batch 18 - Repos 177 to 186 | AB AppDev project, next 10 repos. | 19 Aug 2026 | 20 Aug 2026 | Not Started | 10 AB AppDev repos on GitHub
30 | Phase 5 | Batch 19 - Repos 187 to 196 | AB AppDev project, next 10 repos. | 20 Aug 2026 | 21 Aug 2026 | Not Started | 10 AB AppDev repos on GitHub
31 | Phase 5 | Batch 20 - Repos 197 to 206 | AB AppDev project, next 10 repos. | 21 Aug 2026 | 21 Aug 2026 | Not Started | 10 AB AppDev repos on GitHub
32 | Phase 5 | Batch 21 - Repos 207 to 216 | AB AppDev project, next 10 repos. | 21 Aug 2026 | 24 Aug 2026 | Not Started | 10 AB AppDev repos on GitHub
33 | Phase 5 | Batch 22 - Repos 217 to 226 | AB AppDev project, next 10 repos. | 24 Aug 2026 | 25 Aug 2026 | Not Started | 10 AB AppDev repos on GitHub
34 | Phase 5 | Batch 23 - Repos 227 to 236 | AB AppDev project, next 10 repos. | 25 Aug 2026 | 26 Aug 2026 | Not Started | 10 AB AppDev repos on GitHub
35 | Phase 5 | Batch 24 - Repos 237 to 246 | AB AppDev project, next 10 repos. | 25 Aug 2026 | 26 Aug 2026 | Not Started | 10 AB AppDev repos on GitHub
36 | Phase 5 | Batch 25 - Repos 247 to 256 | AB AppDev project, next 10 repos. | 26 Aug 2026 | 27 Aug 2026 | Not Started | 10 AB AppDev repos on GitHub
37 | Phase 5 | Batch 26 - Repos 257 to 266 | AB AppDev project, next 10 repos. | 26 Aug 2026 | 27 Aug 2026 | Not Started | 10 AB AppDev repos on GitHub
38 | Phase 5 | Batch 27 - Repos 267 to 276 | AB AppDev project, next 10 repos. | 27 Aug 2026 | 27 Aug 2026 | Not Started | 10 AB AppDev repos on GitHub
39 | Phase 5 | Batch 28 - Repos 277 to 286 | AB AppDev project, next 10 repos. | 27 Aug 2026 | 27 Aug 2026 | Not Started | 10 AB AppDev repos on GitHub
40 | Phase 5 | Batch 29 - Repos 287 to 296 | AB AppDev project, next 10 repos. | 27 Aug 2026 | 28 Aug 2026 | Not Started | 10 AB AppDev repos on GitHub
41 | Phase 5 | Batch 30 - Repos 297 to 306 | AB AppDev project, next 10 repos. | 27 Aug 2026 | 28 Aug 2026 | Not Started | 10 AB AppDev repos on GitHub
42 | Phase 5 | Batch 31 - Repos 307 to 309 | AB AppDev project, final 3 repos. All 309 active repos are now on GitHub. | 28 Aug 2026 | 28 Aug 2026 | Not Started | All AB AppDev repos on GitHub
43 | Phase 6 | CI/CD Repo Identification | Identify which repos need a CI/CD pipeline. Document the pipeline type and trigger pattern for each repo before rollout begins. | 26 Aug 2026 | 27 Aug 2026 | Not Started | CI/CD candidate list approved
44 | Phase 6 | CI/CD Pipeline Rollout | Apply the standard GitHub Actions workflow YAML to all identified repos using apply_cicd.py. Validate that each pipeline runs successfully on the self-hosted runner. | 26 Aug 2026 | 28 Aug 2026 | Not Started | Pipelines active, runner jobs passing
45 | Phase 6 | Full Org Audit | Run post_migration_verify.py across all 309 repos. Every repo must have a project topic, correct default branch, a Ruleset applied, and team access confirmed. | 26 Aug 2026 | 27 Aug 2026 | Not Started | Audit report with all repos passing
46 | Phase 6 | Security Review | Confirm no repos are accidentally public, secret scanning is enabled org-wide, push protection is on, and no hardcoded secrets are flagged. | 26 Aug 2026 | 27 Aug 2026 | Not Started | Security sign-off
47 | Phase 6 | Consumer URL Updates | Update any submodule references, CI clone URLs, and README badges that still point to ADO. Raise pull requests in each affected repo. | 26 Aug 2026 | 28 Aug 2026 | Not Started | All consumers updated to GitHub URLs
48 | Phase 7 | ADO Server Archive | Set all ADO repos to read-only. Send communications to all teams: ADO is now archive-only and will be retained for 90 days. | 28 Aug 2026 | 31 Aug 2026 | Not Started | ADO read-only, comms sent
49 | Phase 7 | Runbook Handover | Hand over the runbook to the platform team covering: how to add a new repo, apply topics, request access, change a Ruleset, and manage the runner. Includes a 1-hour walkthrough session. | 28 Aug 2026 | 31 Aug 2026 | Not Started | Runbook delivered and session completed
50 | Phase 7 | ADO Decommission Planning | Plan the ADO Server decommission for 90 days after archive. Confirm the data retention policy and schedule with the Abank infrastructure team. | 31 Aug 2026 | 31 Aug 2026 | Not Started | Decommission plan signed off

## Decisions Needed
S.No | Decision | Context | Decision Owner | Options
1 | master to main rename | 309 repos use master as the default branch. Do we rename to main during migration or keep master? | Project Lead and Dev Teams | Rename to main during the mirror step (recommended) or keep master as-is
2 | 18 empty repos | 18 repos have no commits. Do we skip them or create empty shell repos on GitHub? | Repo Owners | Skip the empty repos (recommended) or create empty shells on GitHub
3 | 3 name conflicts | ACH BAI File Generator, BAM, and DW STAGING LOAD LEGACY each exist in more than one project. One copy of each must be renamed before migration. | Repo Owners | Add a project suffix to the less-active copy, for example BAM-standalone
4 | Self-hosted runner infrastructure | What server or VM will host the org-level self-hosted runner, and who is responsible for maintaining it? | Abank Infra | Dedicated VM (recommended) or reuse an existing build server
5 | ADO archive retention period | How long should ADO repos remain read-only after cutover before the server is decommissioned? | Abank IT Management | 90 days (recommended), 6 months, or permanent

## Scripts to Develop
S.No | Phase | Script Name | Purpose | Owner | Role in Migration
1 | Phase 1 | git_mirror_migrate.py | Clones each repo from ADO and pushes it to GitHub. Supports dry-run, retry, resume, and master to main rename. | Engineer | Core migration engine
2 | Phase 1 | apply_topics_teams.py | Sets GitHub topics and team permissions for each repo based on the workbook. Dry-run and idempotent. | Engineer | Org hierarchy and access
3 | Phase 1 | apply_rulesets.py | Creates 3 to 4 Ruleset templates and attaches them to repos by topic. Dry-run supported. | Engineer | Branch protection
4 | Phase 1 | post_migration_verify.py | Runs a pass or fail check on each repo: branch count, default branch, topics, team access, and Ruleset. | Engineer | Quality gate per batch
5 | Phase 1 | apply_cicd.py | Applies the standard GitHub Actions workflow YAML to identified repos and confirms the pipeline triggers on the self-hosted runner. | Engineer | CI/CD rollout
6 | Phase 2 | pilot_runner.sh | Orchestrates the full 5-script sequence on the 2 pilot repos. Captures logs and outputs a summary report. | Engineer | Pilot orchestration